## Risk Register
Risk Register
Risk ID | Vendor | Risk Category | Risk Description | Likelihood | Impact | Inherent Rating | Control in Place | Residual Rating | Owner | Target Date | Status
VR-001 | CloudDocs Inc. | Security | Unauthorized access to customer PII | Medium | High | High | MFA, RBAC, encryption | Medium | Vendor Security | 2026-05-15 | Open
VR-002 | CloudDocs Inc. | Operational | Service outage delays customer processing | Medium | Medium | Medium | Availability controls, backups | Medium | IT Operations | 2026-05-30 | Monitoring
VR-003 | CloudDocs Inc. | Logging/Monitoring | Limited log retention reduces visibility | Medium | Medium | Medium | Centralized logging | Medium | Security Operations | 2026-06-01 | Open
VR-004 | CloudDocs Inc. | Access Management | Delayed user access review evidence | Medium | High | High | Periodic review process exists | Medium | Vendor Compliance | 2026-05-20 | Open